## RFP Timeline
FORMAL SOLICITATION TIMELINE ESTIMATOR |  |  |  |  | Expected BOE Schedule
Complete the highlighted boxes to calculate the estimated time necessary to complete a formal solicitation. The Purchasing Division needs a minimum of two-weeks to develop an RFP, the large the project, the longer the lead time. | [8 empty] | When January 1, July 4, November 11, or December 25 falls on a Saturday, the preceding Friday is the observed legal holiday. If these days fall on Sunday, the following Monday is the observed holiday.
Activity | Time to Complete |  | Est. Date | Date | Agency Deadline | Meeting Date |  |  | Date | Holiday | NAC 284.255
Today |  |  | 2024-02-09 | 2024-02-09 | 2023-09-05 | 2023-10-10 | 10 | 2023 | 2024-01-01 | New Year's Day | January 1st
Internal Agency Activity 1 (if needed) | 0 | Weeks from Today | 2024-02-09 | 2024-02-09 | 2023-10-10 | 2023-11-14 | 11 |  | 2024-01-15 | Martin Luther King Day | Third Monday in January
Internal Agency Activity 2 (if needed) | 0 | Weeks from 1 | 2024-02-09 | 2024-02-09 | 2023-11-07 | 2023-12-12 | 12 |  | 2024-02-19 | President's Day | Third Monday in February
Internal Agency Activity 3 (if needed) | 0 | Weeks from 2 | 2024-02-09 | 2024-02-09 | 2023-12-05 | 2024-01-09 | 1 | 2024 | 2024-05-27 | Memorial Day | Last Monday in May
Scope of Work (SOW) & Evaluation Factors | 1 | Weeks from 3 | 2024-02-16 | 2024-02-16 | 2024-01-09 | 2024-02-13 | 2 |  | 2024-06-19 | Juneteenth | June 19th
Deputy Attorney General (DAG) review SOW | 1 | Weeks from SOW | 2024-02-23 | 2024-02-23 | 2024-02-06 | 2024-03-12 | 3 |  | 2024-07-04 | Independence Day | July 4th
Technology Investment Notification (if needed) | 0 | Weeks from SOW | 2024-02-23 | 2024-02-23 | 2024-03-05 | 2024-04-09 | 4 |  | 2024-09-02 | Labor Day | First Monday in September
Agency CCM Review & Approval | 1 | Weeks from DAG | 2024-03-01 | 2024-03-01 | 2024-04-09 | 2024-05-14 | 5 |  | 2024-10-25 | Nevada Day | Last Friday in October
Submit Development Form & SOW | 1 | Weeks from Approval | 2024-03-08 | 2024-03-08 | 2024-05-07 | 2024-06-11 | 6 |  | 2024-11-11 | Veterans Day | November 11th
Formal Solicitation Approval & Release | 2 | Weeks from Dev. Form | 2024-03-22 | 2024-03-22 | 2024-06-04 | 2024-07-09 | 7 |  | 2024-11-28 | Thanksgiving Day | Fourth Thursday in November
Site Visit Registration (if needed) | 0 | Weeks from Release | 2024-03-22 | 2024-03-22 | 2024-07-09 | 2024-08-13 | 8 |  | 2024-11-29 | Family Day | Friday following the Fourth Thursday in November
Site Visit (if needed) | 0 | Weeks from Registration | 2024-03-22 | 2024-03-22 | 2024-08-06 | 2024-09-10 | 9 |  | 2024-12-25 | Christmas Day | December 25th
Deadline for questions 1 | 2 | Weeks from Site Visit | 2024-04-05 | 2024-04-05 | 2024-09-03 | 2024-10-08 | 10 |  | 2025-01-01 | New Year's Day | January 1st
Answers posted 1 | 1 | Weeks from Questions 1 | 2024-04-12 | 2024-04-12 | 2024-10-08 | 2024-11-12 | 11 |  | 2025-01-20 | Martin Luther King Day | Third Monday in January
Deadline for questions 2 (if needed) | 0 | Weeks from Answers 1 | 2024-04-12 | 2024-04-12 | 2024-11-05 | 2024-12-10 | 12 |  | 2025-02-17 | President's Day | Third Monday in February
Answers posted 2 (if needed) | 0 | Weeks from Questions 2 | 2024-04-12 | 2024-04-12 | 2024-12-10 | 2025-01-14 | 1 | 2025 | 2025-05-26 | Memorial Day | Last Monday in May
Deadline for references | 3 | Days before Opening | 2024-04-23 | 2024-04-23 | 2025-01-07 | 2025-02-11 | 2 |  | 2025-06-19 | Juneteenth | June 19th
Proposal opening (evaluation start) | 2 | Weeks from Answers 2 | 2024-04-26 | 2024-04-26 | 2025-02-04 | 2025-03-11 | 3 |  | 2025-07-04 | Independence Day | July 4th
Committee meeting (evaluation end) | 2 | Weeks from Opening | 2024-05-10 | 2024-05-10 | 2025-03-04 | 2025-04-08 | 4 |  | 2025-09-01 | Labor Day | First Monday in September
Vendor presentations (if needed) | 2 | Weeks from Evaluation | 2024-05-24 | 2024-05-24 | 2025-04-08 | 2025-05-13 | 5 |  | 2025-10-31 | Nevada Day | Last Friday in October
Vendor Selection |  |  | 2024-05-24 | 2024-05-24 | 2025-05-06 | 2025-06-10 | 6 |  | 2025-11-11 | Veterans Day | November 11th
Notice of Intent (NOI) / start negotiations | 1 | Day after Presetations | 2024-05-25 | 2024-05-28 | 2025-06-03 | 2025-07-08 | 7 |  | 2025-11-27 | Thanksgiving Day | Fourth Thursday in November
Agree to Terms / end negotiations | 3 | Weeks from NOI | 2024-06-18 | 2024-06-18 | 2025-07-08 | 2025-08-12 | 8 |  | 2025-11-28 | Family Day | Friday following the Fourth Thursday in November
Vendor Signature | 2 | Days from agreement | 2024-06-20 | 2024-06-20 | 2025-08-05 | 2025-09-09 | 9 |  | 2025-12-25 | Christmas Day | December 25th
Deputy Attorney General (DAG) Signature | 5 | Days from vendor | 2024-06-25 | 2024-06-25 | 2025-09-09 | 2025-10-14 | 10 |  | 2026-01-01 | New Year's Day | January 1st
Agency Head Signature | 3 | Days from DAG | 2024-06-28 | 2024-06-28 | 2025-10-07 | 2025-11-11 | 11 |  | 2026-01-19 | Martin Luther King Day | Third Monday in January
Notice of Award (NOA) / Start Appeal Period | 1 | Day from Agency | 2024-06-29 | 2024-07-01 | 2025-11-04 | 2025-12-09 | 12 |  | 2026-02-16 | President's Day | Third Monday in February
GFO/CETS submission |  |  | 2024-07-01 | 2024-07-01 |  |  |  |  | 2026-05-25 | Memorial Day | Last Monday in May
End of Appeal Period | 11 | Days from NOA | 2024-07-12 | 2024-07-12 |  |  |  |  | 2026-06-19 | Juneteenth | June 19th
Projects under $100K | [8 empty] | 2026-07-03 | Independence Day | July 4th
Est. BOE/Clerk approval | 10 | Days from Submission | 2024-07-11 | 2024-07-11 |  |  |  |  | 2026-01-07 | Labor Day | First Monday in September
Contract start date | 0 | Days from BOE | 2024-07-11 | 2024-07-11 |  |  |  |  | 2026-10-30 | Nevada Day | Last Friday in October
Functional production | 0 | Months from Start | 2024-07-11 | 2024-07-11 |  |  |  |  | 2026-11-11 | Veterans Day | November 11th
Projects over $100K | [8 empty] | 2026-11-26 | Thanksgiving Day | Fourth Thursday in November
Est. BOE agenda deadline | Five weeks prior to each meeting |  | 2024-07-09 | 2024-07-09 |  |  |  |  | 2026-11-27 | Family Day | Friday following the Fourth Thursday in November
Est. BOE approval | Second Tuesday of each month |  | 2024-08-13 | 2024-08-13 |  |  |  |  | 2026-12-25 | Christmas Day | December 25th
Contract start date | 0 | Days from BOE | 2024-08-13 | 2024-08-13
Functional production | 0 | Months from Start | 2024-08-13 | 2024-08-13
Formulas:
Est. Date = [Date, row above]+([Time to Complete]*7)
Est. Date = [Date, row below]-3
Date = [Est. Date]
Date = WORKDAY(([Est. Date]-1),1,Holidays)
Agency Deadline = [Meeting Date]-35